## Sheet1
Mobile Pre-Reg App March 2019 timeline
Task Number | Task Title | Type | Task Owned | Start Date | Due Date | Duration | Percent of Task Complete | Planning | [11 empty] | Sprint 1 | [11 empty] | Sprint 2 | [11 empty] | Sprint 3
[8 empty] | Week 1 | [5 empty] | Week 2 | [5 empty] | Week 1 | [5 empty] | Week 2 | [5 empty] | Week 1 | [5 empty] | Week 2 | [5 empty] | Week 1 | [5 empty] | Week 2
[8 empty] | M | T | W | TH | F | S | M | T | W | Th | F | S | M | T | W | TH | F | S | M | T | W | Th | F | S | M | T | W | TH | F | S | M | T | W | Th | F | S | M | T | W | TH | F | S | M | T | W | Th | F | S
1 | Gathering information for system implementation
1.1 | Create Project Title and Topic |  | All | 2019-04-02 | 2019-08-02 | 2 | 100% | bar: Week 1 M to Week 1 F
1.2 | Define Goals and Objective |  | All | 2019-09-02 | 02/15/2019 | 2 | 100% | bar: Week 1 S to Week 2 F
1.3 | Create Initial Process Flow |  | Achas | 02/16/2019 | 02/20/2019 | 2 | 100% | bar: Week 2 S to Week 1 W
1.4 | Design System GUI |  | Villaflor | 02/21/2019 | 02/23/2019 | 1 | 100% | bar: Week 1 TH to Week 1 S
1.5 | Define System Architecture |  | Guilaran | 02/22/2019 | 02/23/2019 | 1 | 100% | bar: Week 1 F to Week 1 S
1.6 | Define Tasks |  | Villaflor | 02/25/2019 | 02/26/2019 | 1 | 100% | bar: Week 2 M to Week 2 T
1.7 | Create Estimates (Timeline) |  | Achas | 02/27/2019 | 02/27/2019 | 1 | 100% | bar: Week 2 W
2 | Development: User Login
2.1 | Login and Validation |  | Casiano | 02/28/2019 | 2019-02-03 | 4 | 100% | bar: Week 2 Th to Week 2 S
3 | Development: Student Clearance input
3.1 | Clearance input |  | Robles | 2019-02-03 | 2019-05-03 | 4 | 100% | bar: Week 2 S to Week 1 T
3.2 | Admin Queue Database |  | Robles | 2019-04-03 | 2019-08-03 | 5 | 100% | bar: Week 1 M to Week 1 TH
3.3 | Admin Queue GUI |  | Robles | 2019-05-03 | 2019-08-03 | 5 | 100% | bar: Week 1 T to Week 1 TH
4 | Development: User Wait Page
5 | Development: Post pre-reg transaction
5.1 | Pre-reg completion Page |  | Malinao | 2019-05-03 | 2019-12-03 | 4 | 100% | bar: Week 1 T to Week 2 T
5.2 | Student COR auto-generate |  | Malinao | 2019-05-03 | 2019-12-03 | 4 | 100% | bar: Week 1 T to Week 2 T